## Project Plan
# | Task | PR | Comment | 8/7/2026 | 8/8/2026 | 8/9/2026 | 8/10/2026 | 8/11/2026 | 8/12/2026 | 8/13/2026 | 8/14/2026 | 8/15/2026 | 8/16/2026 | 8/17/2026 | 8/18/2026 | 8/19/2026 | 8/20/2026 | 8/21/2026 | 8/22/2026 | 8/23/2026
1 | Familiarize with project requirements, mockups & client brief | Both | Reviewed Project1 doc + mockups
2 | Set up GitHub repository & push initial project structure | Hamlet | Repo: Project1-Dieneba-Hamlet
2.1 | Organize folder structure (css/js/images) | Hamlet
3 | Gather & organize assets from shared Google Drive | Dieneba | Logos, images, text content
4 | Review page mockups & plan site navigation | Both | Home, About, Contact, Locations, etc.
5 | Research Bootstrap 4, jQuery/Ajax & Vue integration approach | Hamlet
6 | Assign page ownership & finalize task plan | Both | Elected lead developer
7 | Build Home page (HTML/CSS/Bootstrap) | Dieneba
8 | Build About page | Dieneba
9 | Build Contact page with HTML form | Dieneba | Form + submit button
10 | Build Locations page | Dieneba
11 | Build Swim Programs page | Dieneba | Table for class schedule
12 | Build Swim Lessons page | Dieneba
13 | Build Adult Program page | Dieneba
14 | Build navbar with hamburger menu (all pages) | Hamlet | Bootstrap navbar-toggler
15 | Implement sticky navbar across all screens | Hamlet
16 | Build sign-in page/component | Hamlet
16.1 | Style sign-in form with Bootstrap | Hamlet
17 | Add jQuery component #1 | Hamlet | Min. 2 jQuery components required
18 | Add jQuery component #2 with Ajax feature | Hamlet
19 | Build simple Vue component | Hamlet
20 | Add JavaScript ES5 interactions/behaviors sitewide | Hamlet
21 | Add SEO, meta & other head tags to all pages | Dieneba
22 | Style pass & responsive QA across all pages | Both
23 | Bug fixes & final testing | Both
24 | Final commit, push to GitHub & submit URL | Both | Submit to Dropbox on GAP
Legend:
Dieneba
Hamlet
Both